## Sheet1
Bug Description | Asssigned To | Resolve Time
Slide-1
Should give mssage "The username or password entered is not recognized“ when either the incorrect username or password is entered. | Tushar
Forgot password feature needs completion. | Sukh Pal
Remove “lorem ipsum…” and center the Three Bridge logo. | Tushar
EXTREMELY slow to load profilesupon log-in | Punit
Slide-2
Column is missing label “Name” | Punit
“Latest Update” field data is not showing. Also, remove word “on”. Should just show date and time of last update. | Punit
Activity logs are not showing live data or filtering the list– still hardcoded. | Punit
Spouse data is incorrect – getting many different results. | Punit
Search only works on first name. should work on first and last name for client and spouse. | Punit
Chancel Label “All Clients” to “All Profiles”. When click should reset the list to show all profiles | Punit
Flag should only appear if there is one or more flagged items on a profile | Punit
Click on client name or spouse name should take to profile summary page (side-by-side client/ spouse) | Punit
Must be able to delete a profile. | Punit
Slide-3
Please hide thumnail view for the beta release. It is not working properly and not a priority. | Punit
Slide-4
Added spouse for Mary Smith and for some reason it added the same spouse to Alice west. When I deleted the spouse for Alice it also deleted the spouse for Mary. | Punit
Slide-5
Primary phone and email are not saving to DB | Sukh Pal
Need ability to remove photo that has been uploaded to then show no photo | Sukh Pal
When clicked profile icon it took me to wrong profile. Tried again and it went to correct profile. Not consistent in results | Sukh Pal
Slide-6
State list is incorrect and incomplete | Sakshi
City should be text field not dropdown | Sakshi
Country list is incomplete | Sakshi
When Click “delete” should bring message “Are you sure you want to delete this data?” | Sakshi
Zipcode should be “Postal Code” and should accept letters and special characters | Sakshi
For some reason sometimes Save button does not do anything – I found this problem on all of the popups. | Sakshi
GENERAL: All address fields need to be in international formats
Backlog New Feature – add ability to copy addresses from list of spouse addresses
Slide-7
Fields not in order of requirements. Should be: High School, Some College, College Degree, Graduate Degree, MD/JD/DDS, PhD, Trade School, Enter Other. | Tushar
Primary Field of Study incorrectly displays “Enter” when no value entered. should display blank field (see “Degree”). | Tushar
“:” suddenly went missing between words Study and Engineering then it reappeared. | Tushar
Spouse Education data does not save | Sukh Pal
Slide-8
Year, Earned, Field, Study should be capitalized | Tushar
Slide-9
Spouse profession data does not save | Tushar
Slide-10
Data does not save. Click “Save” button does nothing | Punit
Start, End, and Date should be capitalized | Punit
Slide-11
Does not match order in requirements doc. Should be: Single, Married, Divorced, Separated, Widowed, Domestic Partner, Other
Need to discuss this functionality. Only categories for relationships that have been entered should be displayed. Should also put some summary data for the categories such as Name and Age. No data is saving at this time.
Remove Spouse/Partner. It is conflicting with the spouse data entered via clicking green co-client button
Data does not save
BACKLOG REQUIREMENT – future capability to copy/share relationship from/with spouse
Slide-12
Data does not save when click back to client profile
Add “Lives With You” with Yes and No toggle for response Country and State lists are incomplete
Last name is not required. Only first name is required.
Should have option to delete a relationship
Slide-13
Should show name of family member once past Personal page.
See previous comment about order of marital status items
+ and – icons are not consistent with design
Spacing is off
Should be “Relationships”
Slide-14
Spacing of words looks off. Might need to move to boxes like ones used for Special Requirements
Should be “Terminal Illness”
Should be “Chronic Illness”
Change to “Special Needs”
BUG - Flag does not highlight when clicked
Should be “Minor Problems”
Slide-15
Education Level data inputs design and values should be the same as for client profile
Slide-16
Graduation Year should allow for dates in the future 20 years ahead of current year
See following pages regarding this design
Slide-17
discussion required before making changes
Slide-18
step 1 - click Add School
Slide-19
Step 2 - School input appears. Enter data or remove
Slide-20
Too add another school click “add school” and repeat data input.
To remove entire school click “remove”. Brings message pop-up “Are you sure you want to remove this item?” “Yes” “Cancel” options
To remove data item just click on data item and click delete
To edit data just enter new data and is automatically saved same as other data on page
Slide-21
BUG - Flags do not highlight when clicked
Should not be a dropdowns. All options should be visible to select.
Should not be dropdowns. Should be visible to select – consistent with design of other multi-select items. This should also be multi-select
Change labels to: “Financial Support” and “Financial Gift”
Timing should be day/month/year selectors with ability to select either only year, month and year, or all three.
Add “Frequency” – One-Time, Weekly, Monthly, Quarterly, Semi-Annually, Annually, Other
Slide-22
Only categories with data should display.
Should show list of summary data within each category – Name, Company, Phone Number for each relationship
BUG – Client Context was lost when clicked on professional relationship
FEATURE BACKLOG – future capability to copy/share relationship from/with spouse
Slide-23
When “Other” is available as an option to choose there should always be a text field to enter the details of “other”
Name should be consistent with other name formats throughout application, separate fields for – Pre-fix, First, Middle, Last, Suffix
Address should not be split on two columns. Put all address data together in right column (Company Name through Postal Code. See comments on page 6 regarding address field standards
Move all other data to left column (“Services provided” through “how met”)
Add Other with text entry as additional option to select for “How Met”
Capitalize words - Relationship, Began, Ended
BUG – Client Name is not showing
Should read “Add Professional Relationship for [client name]”
This is hidden from view. I did not even see it there until I went back a third time. Needs to be more clear there is more.
Slide-24
Change to “Rate Your Experience With this Professional”
Capitalize words - You and Recommend
Spacing is off – not sure this is the best design for these questions.
Missing requirements: What do you value in an advisor, What do you value in a Financial Advisory firm, Have you ever fired an advisor, Which type of relationship with your advisors is most appealing to you. See requirements doc for details.
Slide-24
BUG - Add Friend Data is not saving correctly and client context was lost. Logged out and back in and then it saved. Clicked on another view and it disappeared again. Clicked again and it reappeared again. Very inconsistent.
BUG - Year values showing “-1” for no data selected
When no values are selected the fields should be blank, not “select” and “enter” as shown above.
First name only should be required to save data.
If no additional data is entered then fields should be blank
Throughout the application the co-client/spouse data is not saving.
BACKLOG REQUIREMENT – future capability to copy/share relationship from/with spouse
Slide-26
Name should be consistent with other name formats throughout application, separate fields for – Pre-fix, First, Middle, Last, Suffix | Punit
Please add Country | Punit
State List is incomplete | Punit
Change labels to: “Financial Support” and “Financial Gift” | Punit
Timing should be day/month/year selectors with ability to select either only year, month and year, or all three. | Punit
Missing requirement “Type” | Punit
Add “Frequency” – One-Time, Weekly, Monthly, Quarterly, Semi-Annually, Annually, Other | Punit
Notes should be larger so as to be clear that it applies to the entire relationship, not just Financial Support | Punit
Flag spacing is off and flags should highlight when selected. | Punit
Should not be radio buttons. Inconsistent with application design. Change to toggle button | Punit